## gantt
PROJECT TITLE | cse_406
TASK | TASK | TASK OWNER | DURATION | DEPENDANCE | LIMIT DATE | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8
ID | TITLE |  |  |  |  | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4
1 | Organization | bar: WEEK 1 10; WEEK 4 7 to WEEK 5 9; WEEK 8 1 to WEEK 8 4
1.1 | Create a GitHub repository |  | 1d | - | 2025-10-17 | bar: WEEK 1 10
1.2 | Create a KaKaoTalk message server |  | 1d | - | 2025-10-17 | bar: WEEK 1 10
1.3 | Create an AWS account |  | 1d | - | 2025-10-17 | bar: WEEK 1 10
1.4 | Create a Figma workspace |  | 1d | - | 2025-10-17 | bar: WEEK 1 10
1.5 | Create a Google Docs shared folder |  | 1d | - | 2025-10-17 | bar: WEEK 1 10
2 | Documentation | bar: WEEK 4 7 to WEEK 5 9; WEEK 8 1 to WEEK 8 4
2.1 | Write assignement 1 : Abstract, Problem Statement |  | 2d | - | 2025-10-17 | bar: WEEK 1 10 to WEEK 1 11
2.2 | Write assignement 1 : Motivation, Anlyse Existing Products |  | 2d | 2.1 | 2025-10-17 | bar: WEEK 1 12 to WEEK 1 13
2.3 | Write assignement 1 : Requirement, Role Assignement | * | 2d | 2.2 | 2025-10-17 | bar: WEEK 1 14 to WEEK 1 15
2.4 | Arbitrate, understand and write assignement 2 : Developement Environement | * | 8d | 2.3 | 2025-11-07 | bar: WEEK 1 16 to WEEK 2 23
2.5 | Design a Desgin System on Figma |  | 7d | 2.4 | 2025-12-05 | bar: WEEK 3 24 to WEEK 3 30
2.6 | Design a Wireframes on Figma |  | 7d | 2.4 | 2025-12-05 | bar: WEEK 3 24 to WEEK 3 30
2.7 | Write assignement 3 : Architecture Design |  | 3d | 2.5/2.6 | 2025-12-05 | bar: WEEK 4 1 to WEEK 4 3
2.8 | Write assignement 3 : Overall architecture |  | 3d | 5.2 | 2025-12-05 | bar: WEEK 8 31 to WEEK 8 2
2.9 | Write assignement 3 : Directory organization |  | 3d | 5.2 | 2025-12-05 | bar: WEEK 8 31 to WEEK 8 2
2.10 | Write assignement 3 : UML (Sequence diagrams, Activity diagrams, Use cases, Physical data model) |  | 3d | 5.2 | 2025-12-05 | bar: WEEK 8 31 to WEEK 8 2
2.11 | Write assignement 3 : Software Installation Guide |  | 3d | 5.2 | 2025-12-05 | bar: WEEK 8 31 to WEEK 8 2
2.12 | Create video presentation | * | 2d | 2.11 | 2025-12-05 | bar: WEEK 8 3 to WEEK 8 4
2.13 | Create pptx presentation | * | 2d | 2.11 | 2025-12-05 | bar: WEEK 8 3 to WEEK 8 4
3 | Front-End | bar: WEEK 4 7 to WEEK 5 9; WEEK 8 1 to WEEK 8 4
3.1 | Init a folder front with a project React Vite.js |  | 1d | 1.1 | 2025-12-05 | bar: WEEK 1 11
3.2 | Write Index |  | 1d | 2.5 | 2025-12-05 | bar: WEEK 4 1
3.3 | Setup components |  | 3d | 2.5 | 2025-12-05 | bar: WEEK 4 1 to WEEK 4 3
3.4 | Setup translation |  | 1d | 3.1 | 2025-12-05 | bar: WEEK 4 4
3.5 | Integrate Authentifaction (Login, Logout, Registration, Security) |  | 3d | 2.6/4.2 | 2025-12-05 | bar: WEEK 4 1 to WEEK 4 3
3.6 | Create ressource for take a picture from browser and send it to the Back-End |  | 3d | 2.6/3.2 | 2025-12-05 | bar: WEEK 4 1 to WEEK 4 3
3.7 | Integrate the results of the skin analysis |  | 7d | 4.7 | 2025-12-05 | bar: WEEK 5 12 to WEEK 6 18
3.8 | Integrate the method CRUD oriented user for manage fridge |  | 7d | 4.8 | 2025-12-05 | bar: WEEK 5 12 to WEEK 6 18
3.9 | Integrate personal statistics |  | 4d | 4.7/4.8 | 2025-12-05 | bar: WEEK 6 19 to WEEK 7 22
4 | Back-End | bar: WEEK 4 7 to WEEK 5 9; WEEK 8 1 to WEEK 8 4
4.1 | Init a folder front with a project Python Fast API |  | 1d | 1.1 | 2025-12-05 | bar: WEEK 1 11
4.2 | Create a schema Users with method CRUD |  | 4d | 2.4/4.1 | 2025-12-05 | bar: WEEK 3 24 to WEEK 3 27
4.3 | Create a schema for photo uploading |  | 4d | 2.4/4.1 | 2025-12-05 | bar: WEEK 3 24 to WEEK 3 27
4.4 | Create a Schema for personnal storage with method CRUD |  | 4d | 2.4/4.1 | 2025-12-05 | bar: WEEK 3 24 to WEEK 3 27
4.5 | Send photo from API analyzer of skin |  | 4d | 3.6/4.3 | 2025-12-05 | bar: WEEK 4 4 to WEEK 4 7
4.6 | Send photo from API analyzer of food |  | 4d | 3.6/4.3/4.4 | 2025-12-05 | bar: WEEK 4 4 to WEEK 4 7
4.7 | Insert and send the API analyzer of skin result for the Front-End |  | 4d | 4.5 | 2025-12-05 | bar: WEEK 5 8 to WEEK 5 11
4.8 | Insert and send the API analyzer of food result for the Front-End |  | 4d | 4.6 | 2025-12-05 | bar: WEEK 5 8 to WEEK 5 11
4.9 | Securing API (CORS, rate limiting) |  | 4d | 4.7/4.8 | 2025-12-05 | bar: WEEK 5 12 to WEEK 6 15
5 | Deployment
5.1 | Initiating containerization in development with Dockers |  | 1d | 3.1/4.1 | 2025-12-05 | bar: WEEK 1 12
5.2 | Deploy Application on AWS |  | 4d | 3.7/3.8/3.9/4.9 | 2025-12-05 | bar: WEEK 7 23 to WEEK 7 26
5.3 | Automates with Kubernetes |  | 4d | 5.2 | 2025-12-05 | bar: WEEK 7 27 to WEEK 8 30